## Sheet2
Phase | Week | Dates (Mon–Sun) | Key Activities / Deliverables
Preparation | Week 1 | Nov 28 – Dec 4 | Freeze problem statement; finalize architecture draft; supervisor alignment; refine abstract & outline; prepare clean diagram set.
Phase 1: Problem Framing & Design | Week 2 | Dec 5 – Dec 11 | Literature review (FDD, Agentic AI, RAG); finalize detailed architecture; define data flow; outline functional modules; prepare full Plan of Work section.
Phase 2: Environment Setup & Simulation Dev | Week 3 | Dec 12 – Dec 18 | Implement AHU simulator; configure normal and fault profiles; add deterministic noise; generate telemetry.csv + metadata.json; initial testing.
Phase 2: Environment Setup & Simulation Dev | Week 4 | Dec 19 – Dec 25 | Complete producer (Kafka/local queue); finalize simulation scenarios; prepare Mid-Sem Report section; perform internal demo; ensure reproducibility. (Mid-Sem Deadline: Dec 17–21)
Phase 3: Consumer & Windowing Layer | Week 5 | Dec 26 – Jan 1 | Mid-Sem Viva window; implement consumer; buffering logic; sliding/tumbling windows; basic feature extraction; create draft window summary format.
Phase 3 → Phase 4 | Week 6 | Jan 2 – Jan 8 | Complete windowing; refine anomaly rules; begin Static KB: chunk manuals, extract relevant sections, define file structure; write synthetic past cases.
Phase 4 → Phase 5 | Week 7 | Jan 9 – Jan 15 | Initialize Chroma DB; populate manuals + past cases collections; build retriever functions; start Dynamic Memory Layer: indexer design + summary schema.
Phase 5 → Phase 6 | Week 8 | Jan 16 – Jan 22 | Build indexer worker; embeddings + upsert logic; retrieval API for historical context; implement controller skeleton and routing rules.
Phase 6 → Phase 7 | Week 9 | Jan 23 – Jan 29 | Complete controller pipeline; implement Stage 1/Stage 2 retrieval; add confidence scoring; implement refinement trigger; start LLM reasoning layer. (Final Report Deadline: Jan 28–Feb 1)
Phase 7 → Phase 8 | Week 10 | Jan 30 – Feb 5 | Finish hierarchical RAG reasoner; design diagnosis schema; reasoning trace + evidence IDs; implement ticket generator; create SQLite tickets.db.
Phase 9: Streamlit Dashboard | Week 11 | Feb 6 – Feb 12 | Develop UI: scenario runner, live telemetry chart, window summaries table, tickets board, ticket detail page; integrate evidence + reasoning view; final polish.
Phase 10: Evaluation & Packaging | Week 12 | Feb 13 – Feb 16 | Evaluation: baseline vs hierarchical RAG; compute metrics; generate plots; package code + documentation; prepare final PPT; viva rehearsal; Final Viva.